## Sheet1
New bug
BUG_ID | Function | BUG Discription | Expected | Actual | URL | SnapShot
1 | Mailer on mail verification | Email didn't received on client mail | OTP verification mail has to be received at client mail. | Did not get any mail
2 | Video KYC | New session created while clicking on GET started button | after completing the KYC step need to get back to the previous session and show further process there | The previous session showed still the same after completing the whole KYC steps | http://178.238.234.59:9851/#/onboading-kyc/video-verify
3 | Video KYC | After successfully updating the Video KYC the proceed to next button is not enable | Proceed to next button has to be enable for the next step | Did not enable
4 | E-sign | E-sign is not verified but the proceed to next button is enabled and after showing a message "Your profile is under verification" | Proceed to next button no need to enable | Button enabled
5 | Order limit on Trade | Need to add validation while selection trade quantity | We can choose the trade volume as we set the minimum quantity | we can choose (0) as Trade quantity | http://178.238.234.59:9851/#/p2p
6 | Make Order | While making order need to add date and time single controller | Need to add time & date in single TAB | Now we have to choose Date & Time in 2 different tabs | http://178.238.234.59:9851/#/p2p
7 | My positions | Need to add User Type column in all sections | User type column has to be added to filter user type | No column has added there | http://178.238.234.59:9851/#/trade
8 | PayG | Payment gateway is not working | it should be redirecting us on Payment page | Error Given by Payment gateway
9 | Get user package | package id is showing (0) | need to get the package data behalf on pkgid | pkgid showing (0)